## Complaints & Incidents Register
HammondCare Greenwich Construction Complaints Register
Project Name: Greenwich Hospital Redevelopment |  |  | Application Number: | SSD-13619238
Project Address:97-115 River Road, Greenwich, NSW 2065 |  |  | Dates: | 1/08/2026 - 31/08/2026
Notes: All complaints made are to be formaly issued via the HammondCare operator on 1300 426 666 or via email at askgreenwich@hammond.com.au.
ID | Description of Complaint | Is This an External Complaint? | Date of Complaint | Action Required? | Outcomes/ Resolve | Close Out Date (if applicable)
1 | As a neighbour and a mother of a child who attends Greenwich Public I wanted to reach out to you about both communication and safety during the construction phase of the hospital. Construction impacts many people who live in the vicinity of sites, that is not something that can be avoided, but it can be managed. What I'm suggesting is that you do a quick letterbox drop and use your web page Planning for the Future – Greenwich development (or better still create a page specifically for the construction period) to communicate things to neighbouring properties as well as provide a contact if there are any concerns. This will potentially reduce the number of calls to Council as well as maintain a positive relationship with your neighbours. I also note that condition A29 refers to documents being made publicly available on your web page but have not been able to find anything that demonstrates compliance. In addition to the above, on my drive to work I noticed a truck parked in the driveway on River Road but it was projecting out past the boundaries of the site and was forcing school children to walk around the front of the truck within close proximity to River Road. I was extremely shocked to see this. There was no traffic control. I appreciate that Hammondcare has engaged a builder to carry out the works, but it is in everyone's best interest that there safety provisions are put in place. You may also want to look at the site fencing which has been placed so it's leaning up against the neighbours wall on St Vincents Road as well as leaning on the mesh fence on St Vincents which looks like it will collapse at any time. I look forward to improved communication and safety. | Yes | 2025-05-09 | Temp fencing along St Vincents road to be moved clear of the ajoining building. HCA Disruption notived to be made avalable on the the Greenwich Development site. HCA note that letter box drops have been conducted. Hindmars-GCOR-000160 | Fence panel has been remove (see attached) and a formal response has been issued via the HammondCare facility to the neighbour. | 2025-05-11
2 | Noting that this was not a formal complaint but a request from a neighbor seeking advice on the duration of vacume truck works happening as part o fthe sewer upgrade between Pallister House and the Gore st Properties. | Yes | 2025-05-14 | HCA to provide advise to HC/TSA with regard to duration of works. TSA/HC to issue advice to the neighbour. | Advise passed back to the complainies | NA
3 | It is difficult for our transport to drive now allowing 3m wide access due to curve hills position. Can we please meet on sites and discuss which gives me clearer picture of the future work, and possible we can break the stages into small one to allow space for Ambulance ? | No | 2025-06-20 | HCA has now pulled the barriers back to what we’ll call the after-hours setup. This setup needs to be in place whenever the team finishes for the day, and the roadway must be swept clean before leaving site. As we move around the bottom corner, this section will need to be hotmixed and finished off before we can continue under the awning area. | NA | NA
4 | Dear Project Management Team, This is a complaint about the obtrusive light evident overnight during this week, coming from the exterior security lighting operating around your site construction huts precinct. The lighting is very bright and quite invasive. Overnight, it shines into my home, on the east side of Northwood. After dark when I went there to photograph the site contact details, I noticed the lighting would also be extreme for others in the vicinity. Natural environment biota will be negatively impacted, as would star-gazing. Would you please address this issue. Perhaps consider placing the lighting further away from the huts, and shine it in the opposite direction - at your huts and fences instead. thank you for your attention to this matter, Jennifer Schneller | Yes | 2025-07-30 | Further investigations to confirm exact source of lighting causing the trouble | I’ve completed a walk-around inspection with Nathan from HammondCare, during which he adjusted two of the carpark floodlights. The most prominent light source visible from Upper Cliff Road was confirmed to be the floodlight mounted to the maintenance building, which Nathan advised was only recently replaced. This supports the likelihood that the neighbour’s concerns relate to a more recent change, rather the the lighting associated with our site sheds, which have been in place for some time. I’ve attached updated photos for reference. Sally / Dave – hopefully this adjustment is enough to alleviate the neighbour’s concerns. | 2025-07-31
5 | Hi Team, I hope you're having a nice afternoon. I’m writing to address the noise from the metal panels on Greenwich Road, which is causing significant disruption to our elderly residents. As an aged care facility, it’s crucial that we maintain a peaceful environment, and the loud rattling from passing vehicles is affecting the well-being of our residents. Our maintenance officer has suggested bolting the panels down to reduce the noise. If that’s not possible, we’d appreciate any other solutions you can provide to help minimise the disturbance. Thank you for your attention to this matter. We look forward to your prompt response. Kind regards, Mary Pang Administration | Yes | 2025-08-15 | To review road plates for better suited plates for the road shape | Roadplates were replaced during night shfit on 17/08/25 with larger 4m units. Upon review the new plates performed much more quietly | 2025-08-17
6 | To whom it may concern I wish to report my concern at the significant pooling of water along our garage / loft as a result of the hospital (in the process of removing asbestos found on their property) digging a trench along our boundary with no drainage provided. The attached photo demonstrates the significant pooling which has never been there before and certainly not before the trench was dug a matter of weeks ago. My concern is that if this is not fully corrected (correctly drained) current and future pooling will result in the undermining of our garage / loft building, water seepage into the building (especially the loft) and the potential of damp / mildew of the wall in our loft area. Accordingly, I am looking to the hospital to totally rectify this issue (caused by them - digging the trench)) and look forward to advice on your proposed solution and timeframe in completing the task. I have raised this issue with the site manager Jack Isemonger. I look forward to your favourable response in the near future. Kind Regards Stephen Loomes | Yes | 2025-08-22 | HCA Notes: he depression along the neighbour’s property line existed prior to our appointment on site. Two weeks ago, our team cleared foliage and asbestos material in this area as part of the removal works (predominantly a large rubble pile in the middle of the depression) however the depression against the building was already present. .The area has historically been lower than the adjoining footpath and effectively landlocked. This was likely exacerbated by the recent heavy rainfall following the removal of ACM material at the upper level.Our overland flow diversion berm is scheduled for installation within the next fortnight;The dilapidation report of the garage, prepared under the SSDA conditions, photos show significant effervescence along the floor and wall of the garage – however this was not noted as a point. This remains evident during my discussion with Stephen last week where we checked there was no surging of the water through his garage. In light of the above, HCA will install an agline against the garage and create falls out to the rioad with drainage backfill material as discussed with the Neighbour onsite | Drainage and backfilling has been completed | 2025-09-25
7 | Hi there I am the owner of 47 Gore Street which backs onto the hospital. I just wanted to bring your attention to a water run-off issue. The new Lily Pilli hedge which backs onto our house is funnelling rainwater through our back gate. Is there a way you could investigate a water management solution as the back area of our house has a 1/2 centimetre thick layer of mud & dirt which has been swept in by the stormwater run-off down the hill? Attached some photos below. Thanks Lewis | Yes | 2025-09-12 | To recontinue Berm works as per design across the rear boundary with no planting installed to allow access through the gate | Berm has been extended across the face of the fence/gate line 18/09/2025 as per initial design | 2025-09-18
8.1 | Resident of No4 S Vincents Street called the hospital to make a noise complaint regarding plant noise during the night shift of S73 works. No written record of complaint only verbally communicated over phone to HammondCare staff | Yes | 2025-10-13 | Hindmarsh to investigate complaint further and speak with neighbour | 13/10/2025 10.19am_Khima called Greg B to report No4 St Vincents made a minor complaint about Nightwork noise in front of their property 10.25am_GB/BG visited No 4 and met Gabi. • Gabi (Occupant) informed us her Daughter was studying for her HSC 11.00am_GB reviewed Letterbox memo with BadenG (Area on plan was not highlighted) and called Blake Cox (Williams Bros) to enquire GB informed by BC that there is correspondence Via JayC and Lane Cove Council that the location was imposed on to (1) Setback from River Road and (2) On the side opposite overhead power lines 11.03am_GB returned with BG and spoke with Gabi explaining the reasoning above. Also agreed that this was not highlighted on the memo. 11.05am_Gabi was grateful and mentioned she would call Lane Cove Council
8.2 | Formal written Complaint made through AskGreenwich complaining of the noise of s73 nightworks in front of 4 St Vincents Road | Yes | 2025-10-14 | Hindmarsh to review | Compound in front of 4 St Vincents Road was decommissioned 16/10 and HCA maintained communciations with neighbours who have not since raised issues | 2025-10-21
9 | Hi, During the water pipe replacement work recently at River Road Greenwich, the driveway of my property at 102 River Road got damaged. May I please know when the damaged driveway will be repaired? According to one of the workers that worked on the water pipe replacement last night, the councils should be fixing all the damaged driveway and footpaths, however, he does not know when. Regards | Yes | 2025-12-05 | Council to rectify | Council inspected and marked extent of driveway repair. To be actioned by Lane Cove Council in the new year | 2025-12-11
10 | We are letting you know that at approx. 7:15am this morning 19/12/26 we witnessed a very large RED construction crane gong up your private driveway in St Vincent Road Greenwich. THIS ROAD MUST NOT BE USED BY CONSTRUCTION VEHICLES AT ANT TIME - IS ANYONE LISTENING AT HAMMONDCARE?? According to the last email we received from you your contractors were meant to be advised NOT to use this driveway We await your reply | Yes | 2026-01-19 | The latest of these documents have been again re-issued to all direct contractors to reinforce no use for medium or heavy vehicles on St Vincents for stage 1 of the project, and a hazard also raised internally. | Hindmarsh Response: We’ve reviewed our cameras onsite and can confirm an indirect subcontractor has likely used St Vincents roadway to enter site for our lift at the substation yesterday. The works were contracted to Wilken, whom have subcontracted the cranage component to Borgers. We can confirm the following steps were in place; • Both Borgers workers had already completed their pre-induction which includes the below snipped information relating to no use of Vincents. (Current doc Ver R8) • Delivery instruction leaflets have been issued to Wilkens on 13/03 (Ver R2) and 02/09 (Ver R3) both clearly showing no heavy vehicles are permitted from Vincents. • Traffic controllers were onsite and established at substation, however the crane continued past the traffic control and was assumed to be for another project. • Wilken workers were onsite and run through the daily prestart held around 0700 – attached 2 of photos showing note for vehicle entry on gate H2, and no use of St Vincents clearly marked. | 2026-01-20
11 | Resident raised concern regarding the upcoming Lane Cove Council footpath upgrade works and the lack of information about alternate pedestrian routes during the works. Resident noted that many Greenwich Public School children use this route to walk to school and raised concern that children may attempt to cross River Road rather than use a longer detour. | Yes | 2026-04-16 | HammondCare/project team to review the resident’s concern and clarify the appropriate source of information for alternate pedestrian routes during the Council-managed footpath works. | HammondCare responded on 20/04/2026 advising that the footpath upgrade works are being managed by Lane Cove Council, and that the most accurate information about alternate pedestrian routes should be obtained directly from Council. HammondCare noted that impacts to footpath access are understood to be kept to a minimum and that adequate support should be in place to ensure continued pedestrian use during the construction period. | 2026-04-20
12 | Resident raised concern regarding Hindmarsh’s notification of proposed removal of 8 trees along River Road. Resident queried why trees outside the hospital grounds were being removed, whether Council approval was required, the urgency of the works, and raised concerns regarding loss of outlook/privacy, night works noise, power disruption, local amenity and wildlife impacts. Resident followed up again after the April project update did not address the tree removal concerns. | Yes | 2026-04-27 | Project team to review the resident’s concerns, confirm the approval basis for the River Road tree removal works, and provide information to HammondCare to support a response. Copies of the neighbour notification/letterbox-drop were provided by HammondCare project team. | HammondCare responded on 30/04/2026 advising that the tree works form part of the approved Greenwich Hospital redevelopment and are authorised under the SSD consent issued by the NSW Department of Planning. The specified trees are included in the approved Tree Retention and Removal Plan, and the consent allows the works, including approved out-of-hours works, to proceed without separate Council approval. HammondCare also directed the resident to the Greenwich redevelopment website for project documentation and acknowledged the impact of the works on the local area. | 2026-04-30
13 | Resident raised concern that communications provided to date have lacked sufficient detail regarding construction staging, including the scope, location, timing of works, and potential impacts such as noise, dust, and vibration. They noted that previous advice from Hindmarsh did not, in their view, align with the requirements of the DPHI Out-of-Hours Work approval conditions, and that recent project updates have been too high-level to allow nearby residents to anticipate impacts. The resident has requested more detailed and timely information in future communications, as well as a copy of the dilapidation report prepared for their property. Inconsistencies between the Staging Report and continued hospital function were also raised. | Yes | 2026-05-22 | Project team to review the resident's concerns, confirm actions conducted to-date and provide information to HammondCare to support a response. | HammondCare responded on 2/06/2026 advising that Stage 1 of the Greenwich redevelopment was completed in January 2026, enabling the commencement of Stage 2 works by Hindmarsh. Essential services have been relocated off-site within the Northern Sydney area to minimise construction risks and disruption to operating hospital functions, while maintaining continuity of care. The project is being delivered in staged works, with a commitment to provide advance notice of potentially disruptive activities such as noise, dust, or vibration, all of which are managed in accordance with approval conditions and mitigation measures. HammondCare also directed the resident to project updates via the newsletter and website and invited further enquiries as needed. | 2026-02-06
14 | Resident reported a strong sewerage odour in their backyard and raised concern that it may be related to previous incidents involving sewerage pipe blockages and overflows within the hospital precinct. The resident requested that the source of the odour be investigated and appropriate action taken to rectify the issue. | Yes | 2026-07-03 | Project team to review the resident's concerns and explore mitigations where possible. | HammondCare responded on 13/07/2026 advising that the construction contractor had investigated reports of an odour potentially associated with the redevelopment works. Multiple site inspections did not detect any sewerage odour, and no issues were identified with the upgraded sewer connection infrastructure associated with the redevelopment. The response noted that investigations had not identified any concerns relating to the works and that the source of the reported odour could not be confirmed. Ongoing monitoring and further investigation were advised should the issue recur. | 2026-07-13
15 | Resident living opposite the construction site reported a continuous droning noise that has recently become more noticeable and disruptive. They queried whether the noise may be originating from site equipment, such as dust suppression machinery or a generator, and requested investigation into its source. The resident also requested that measures be implemented to reduce noise impacts, including addressing any equipment faults or maintenance issues, enclosing or insulating noisy plant and machinery, and considering additional noise mitigation solutions. | Yes | 2026-07-02 | Project team to review the resident's concerns and explore mitigations where possible. | HammondCare responded on 08/07/2026 advising that the construction contractor had investigated reports of a droning noise potentially originating from the redevelopment site. The response noted that continuous noise monitoring had been undertaken since the commencement of construction works and that no noise exceedances had been recorded. A review of monitoring data and site observations did not identify any significant construction noise impacts or equipment faults. HammondCare also advised that noise monitoring and mitigation measures, including acoustic screening, would continue throughout the construction period. | 2026-07-08
16 | A resident located immediately east of the site raised concerns regarding dust impacts associated with demolition works, reporting reduced air quality at their property and the accumulation of dust on recently cleaned windows. The resident noted their belief that prevailing westerly winds may be contributing to dust at their property and requested that additional measures be implemented to minimise dust generation and impacts on neighbouring residences. | Yes | 2026-07-17 | Project team to review the resident's concerns and explore mitigations where possible. | HammondCare responded on 21/07/2026 advising that the construction contractor had investigated concerns regarding dust from the Greenwich Hospital Redevelopment works. The response noted that dust suppression measures, including water spray systems, were being used on site and that dust monitoring along the eastern boundary had recorded no significant dust levels, with air quality remaining within the “good” category. HammondCare also advised that dust suppression and monitoring would continue throughout the works. | 2026-07-21
17 | Complaint received via Lane Cove Council Rangers regarding emergency lighting at the site causing disturbance to nearby residents during nighttime hours. | Yes | 2026-07-08 | Project team to investigate the installation of additional shade cloth to better shield nearby residents from the lighting, along with the potential use of sensors and timers. | Hindmarsh confirmed 20/7/2026 that installation of shade cloths have been completed. Lights have also been automated to turn on at 5 AM and off at 7 PM. | 2026-07-20
18 | A resident raised concerns that vehicles appearing to be associated with the construction site were parking close to both sides of a driveway, reducing visibility and limiting the space available to safely exit and merge onto River Road, particularly during busy morning traffic periods. The resident requested that workers be reminded to leave sufficient clearance near driveways to maintain safe access. 20 Aug 2026: Resident had provided additional images of vehicles parked on River Rd. | Yes | 2026-07-25 | Project team to review the resident's concerns. | HCA notified subcontractors of the complaint and reiterated the parking requirements contained within the Construction Worker Travel and Parking Management Plan. The plan has been issued to all subcontractors and promotes the use of public transport while minimising impacts on surrounding residential streets. HCA will continue to reinforce these requirements with site personnel. River Road is a public road and vehicles parked in the area may not necessarily be associated with the project. HammondCare responded 19/08/2026 relaying the above actions. 20/08/2026 HammondCare provided an additional response to the followup: HammondCare advised that the matter had been raised with contractors, parking expectations would continue to be reinforced with all site personnel, and while parking on public roads cannot be controlled, workers would be reminded to park considerately and be mindful of local residents. | 2026-07-27
19 | I live near the Greenwich Hospital redevelopment site at 97–115 River Road. Over the past two weeks, construction works on the site have resulted in significant dust settling across my property, including outdoor surfaces, paths and steps. I've attached a photograph showing the extent of the dust as evidence. I understand the works are being carried out under the approved State Significant Development consent and the project's Construction Environmental Management Plan (CEMP), which includes dust suppression requirements. Based on the visible dust accumulation on my property, it does not appear these measures are being adequately applied. I would like this resolved urgently. Specifically, I am requesting: 1. Immediate reinforcement of dust suppression measures on site (e.g. water carts, covering of stockpiles/excavated material) — within 24–48 hours. 2. A confirmed date for professional cleaning/wash-down of the affected areas of my property. 3. A response from a site representative (construction/project manager) within 48 hours of this email, including a direct contact for follow-up. Please treat this as a formal complaint and confirm it has been logged in the project's complaints register. If I don't receive a substantive response within 48 hours, I will be escalating this to Lane Cove Council's compliance team and the NSW EPA. I will also be calling to follow up on this today. I look forward to a prompt resolution. | Yes | 2026-08-03 | Project team to review the resident's concerns. | Hindmarsh met with resident on 4/08/2026 to further discuss raised concerns. Written response issued 5/08/2026. Response included the following details: Dust-supression measures along the northern boundary have been increased, including the use of additional water cannons. Dust monitor located near the property has been reviewed and showed no elevated particulate levels near Gate 2 over the past two weeks as of 4/08/2026. The site team will continue to monitor conditions and adjust the dust-supression measures accordingly. | 2026-08-05
20 | Afternoon Jay, I have just had a parent notify me that there is a lot of dust coming from the construction site, without any sprinklers running to dampen the dust. The issue is I have students out on the school oval and netball court, some with asthma, and the dust is causing a concern for the health of the students. I am not sure what the regulations are in terms of spraying water to dampen the dust but if there are times when there is a lot of dust being created it would be good to know so that I can keep the students inside to ensure no health issues arise from the dust inhalation. Is this a possibility? I have cc'd my P &C President in the email so they are aware of the situation. | Yes | 2026-08-14 | Project team to review the concerns. | Hindmarsh provided an interim response advising that dust suppression measures are actively implemented across the site, including the use of water spray systems. Photographic evidence was provided to illustrate current controls, noting that water mist may at times be mistaken for dust. Air quality monitoring results from the dust monitor located on the River Road boundary were also reviewed and indicated particulate levels remained below the National Environment Protection (Ambient Air Quality) Measure limits. Hindmarsh will continue to investigate the concern and provide a further response outlining any additional actions or mitigation measures as required. | 2026-08-14
21 | We are writing to you about the intolerable noise, pile driving and dust emanating from the Hammodcare Hospital redevelopment Something needs to be done about the air pollution as ourselves and neighbours in St Vincents Road (south ) Greenwich have our cars and houses covered in dust from this site, children of our neighbours cannot go out of their houses due to the excessive dust. Something needs to be done NOW | Yes | 2026-08-12 | Project team to review the resident's concerns. | Hindmarsh responded to the resident's concerns and advised that additional dust suppression measures had been implemented across the site, along with increased road sweeping along River Road and St Vincents Road. Dust monitoring results for the preceding week were reviewed and did not indicate elevated airborne dust levels. Hindmarsh confirmed that monitoring and dust control measures will continue to be reviewed and adjusted as required and offered to meet with the resident to discuss the concerns and site mitigation measures in further detail. | 2026-08-14
| Thank you for your note. You wrote: Following your enquiry, we requested Hindmarsh, the construction contractor, to investigate the matter. The contractor has assured us that effective dust suppression measures, including water spray systems, are being used regularly throughout the works. Additionally, the site hoarding and existing vegetation along the eastern boundary provide an extra barrier between the work area and neighbouring properties. I attach a photo I took last week of a car in our drive (14 th August), which my son washed the day before. It does suggest that despite assurances from your contractor that they have “effective dust suppression measures”, that is in fact not the case. I beg you to have them take the issue seriously. Re parking, your 20 August newsletter noted “Construction workers are required to use designated parking arrangements and are advised during site induction not to park in surrounding residential streets.” The western side of St Vincents Road is parked solid with people wearing hi viz from between 6am and 7am, so I don’t think this is working. They are also prone to parking on the eastern side, on and off the pavement, making the street dangerously narrow. Please can you revisit this? Regards, | Yes | 2026-08-21 | Project team to review the resident's concerns. | HammondCare replied on 26/08/2026 advising that dust suppression measures remain in place across the site, including water cannons, sprays, water carts and street sweeping. Dust monitoring results were reported to be below relevant criteria, and the contractor was requested to continue monitoring and adjusting controls in response to reported dust impacts at St Vincents Road. Concerns regarding worker parking on St Vincents Road were also raised with the site team, with personnel and subcontractors to be reminded of approved parking arrangements, road rules and parking restrictions. | 2026-08-26
22 | Dear HammondCare, I appreciate the regular updates you are providing as the details help understand the situation. I am at Gore St so neighbour the hospital grounds. I just wish to bring two items to your attention. Firstly, there have been a couple of times we have had to close our windows due to dust in the air from your construction. It was visible to the eye that there was a general dust cloud. I know you are implementing dust suppression systems I am just highlighting that they don't always work and have impacted us. How dirty the streets are around the hospital just highlight this. I know it can't be avoided for progress but the progress still has an impact. Secondly, you may have included onsite induction training for workers to not park in the surrounding streets but this is not occurring. We were originally told that adequate off street parking would be provided for construction workers to not impact our streets. This does not appear to be the case. I regularly see vehicles parked in Gore St and St Vincents Rd and construction workers leave and walk to Greenwich Hospital. We have a lack of parking on Gore St to begin with as one side is no parking to allow traffic movement. Also vehicles are being illegally parked on St Vincents making two way traffic not viable. Again just bringing this to your attention. Kind regards | Yes | 2026-08-24 | Project team to review the resident's concerns. | HammondCare replied on 26/08/2026 advising that dust suppression measures, including water cannons, water sprays, water carts and street sweeping, are operating across the site and surrounding road network. The response noted that dust monitoring is undertaken around the site, with recent results remaining below the relevant air quality criteria, and that controls are adjusted as required in response to site activities and weather conditions. HammondCare advised that reports of visible dust leaving the site had been referred to the site team for further monitoring and review of mitigation measures. The response also noted that construction traffic and site access are being managed in accordance with the approved Construction Traffic Management Plan, with workers and subcontractors regularly reminded of approved parking arrangements, parking restrictions and road rules. Concerns regarding worker parking on Gore Street and St Vincents Road were raised with the site team for investigation and ongoing monitoring.Parking Management Plan to be continued to be emphasised to workers. | 2026-08-26
23 | Good morning, I am making a formal complaint regarding the intense pounding and low frequency vibrations as well as the incredible amount of dust/particles that the site at River road is creating. I live and work directly opposite the site and am continually finding an abnormal amount of dust covering every surface and appliance in my office and home. Can you please provide a very detailed plan and actions your contractor is utilising to deal with this situation. It's now been 3 or so weeks of excavations and the local environmental conditions are now intolerable! The water spray/s currently being used are obviously not working appropriately! I have spoken with a number of my neighbours and they are experiencing exactly the same as myself. One of them has a new-born baby and they are finding this incredibly difficult! How much longer is this part of the schedule planned and what plans are in place for further protection of the surrounding community? Regards, | Yes | 2026-08-24 | Project team to review the resident's concerns. | HammondCare replied on 26/08/2026 advising that dust suppression measures, including water carts, water cannons, sprays and street sweeping, remain in operation across the site, with dust monitoring results reported to be below relevant air quality criteria. The response noted that excavation, piling and other construction activities may generate intermittent noise and vibration impacts, however works are being undertaken within approved construction hours and in accordance with the project's noise and vibration management requirements. The contractor was requested to continue reviewing and adjusting mitigation measures as required, with high-impact excavation and groundworks currently expected to continue until approximately March 2027. | 2026-08-26
24 | Thank you for your note. By way of example, I am looking right now at a row of Chalojhi utes parked on the western side of St Vincents Road. They are, with respect, fairly obvious. | Yes | 2026-08-26 | Project team to review the resident's concerns. | HammondCare replied on 02/09/2026 advising that workforce parking and construction traffic are being managed in accordance with the approved Construction Traffic Management Plan. The response noted that parking and traffic requirements are communicated through site inductions and ongoing workforce briefings, with workers regularly reminded to comply with parking restrictions, road rules and approved site access arrangements. Workers are encouraged to utilise public transport, active transport, rideshare and other coordinated transport options where practicable. The project team further advised that local parking conditions continue to be monitored, management measures are regularly reviewed, and the concerns raised have been referred to the site team for ongoing awareness and reinforcement. | 2026-09-02